## uat_issues
Sno. | Date | Repetitive Count | Repetitive Dates | Type | Issue | Portfolio Demo | Diabetes | TMW | MDR | EDL | STF | IPRG Demo | image | Video | Remarks | Dev Status
1 |  |  |  | Issue | (Curated Patent)When clicking the Column Dropdown, selecting and then unselecting "Publication Number" and "Other Publication Number" columns causes the left-side columns (Family Grouping and Multiple Patent Select) to disappear when scrolling. | Yes | Yes | Yes |  | Yes | Yes | Yes
2 |  |  |  | Enhancement | (Curated Patent) If I set "Patents per Page" to 100 and delete a patent, it automatically resets to 25.When I set it back to 100 and restore a patent, it again defaults to 25 automatically. | No | No | No |  | No | No | No
3 |  |  |  | Enhancement | (Curated Patent)In the Rating and Ease of Detection sections, when deleting a selected comment, the system shows "Update successfully, The correct message should be "Successfully deleted". | No | No | No |  | No | No | No
4 |  |  |  | Issue | When searching by patent publication date in the search section, the screen remains empty after loading. | No | No | No |  | No | No | No
5 |  |  |  | Issue | (Curated Patent) Sometimes, when selecting Product/Company in the Licensing/Litigation section, the screen appears empty. | Yes | Yes | Yes |  | Yes | Yes | Yes
6 |  |  |  | Issue | (Curated Patent)In the Focus Level section, the tag limit should be 40 characters.However, if I enter more than 40 characters, the Upload button remains clickable, which is incorrect. | No | No | No |  | No | No | No
7 | 2025-09-09 | 2 | 9/9/2025 ¦ 13-10-2025 | Issue | We receive a red error when adding a new tag, and the Delete and Undo buttons also do not work, showing a red error. | No | Yes | Yes |  | Yes | Yes | No | #VALUE!
8 |  |  |  | Enhancement | (Organisation Curation)In the Organisation Curation section, if I add a new company without providing a Company URL, why does the system still display a LinkedIn link? | Yes | Yes | Yes |  | Yes | Yes | Yes
9 |  |  |  | Issue | (Organisation Curation)In the Organisation Curation section, after filling all the required fields and saving the company, the Company Innovation field appears with pre-selected value, However, the selected Company Innovation fields are not visible. | Yes | No |  |  | No |  | No
10 |  |  |  | Issue | (Organisation Curation)In the Company Innovation fields, at Level 2, some categories/tags are shown multiple times.This is incorrect, as each category/tag should appear in only one group. | No | No |  |  | No |  | No | #VALUE!
11 | 2025-08-10 |  |  | Issue | [Portfolio Demo] – Automobile, Automobile Test :When I go to the Un-curated Patents section and select a patent, I proceed to add its Focus Level and Last Level to convert it from an uncurated to a curated patent. However, when I try to add tags, a red error message appears. | No | Yes | Yes |  | Yes | Yes | No
12 | 2025-08-10 |  |  | Issue | [Portfolio Demo] – Automobile Test (Organizing Curation – Company Innovation):When I try to add any link, a red error message appears first. After that, a confirmation message appears indicating that the company link has been successfully saved. | No |  |  |  | No |  | No
13 | 2025-08-10 |  |  | Issue | [Portfolio Demo] – Automobile Test (Organizing Curation – Company Innovation):When I delete any link, it is successfully removed; however, the associated date is not deleted. | No |  |  |  | No |  | No | #VALUE!
14 | 2025-08-10 |  |  | Red Error | [Diabetic] – US2025082840A1:This is an un-curated patent. I curated this patent by adding the Last Level to verify the movement, which was completed successfully. After that, I searched for the patent in the Curated section and confirmed that it appeared correctly, but I searched with Patent ID Red error show. Next, to move it back from Curated to Un-curated, I deleted the Last Level and checked the movement, which was also completed successfully. Finally, I searched for the patent to ensure there were no duplicates in the Curated section. However, when I checked this patent under the ALL section, after waiting for a long loading time, a red error appeared, which should not have occurred. | No | No |  |  | Yes | Yes | No | #VALUE!
15 |  |  |  | Issue | After adding a new company and checking the Dashboard, the 3x3 chart is displayed below the Key Market section. | Yes | Yes | Yes |  | Yes | Yes | No
16 |  |  |  | Issue | (Curated Products)If I add a taxonomy in the Last Level section of a product, the screen keeps loading indefinitely. | Yes | Yes | Yes |  | Yes | Yes | Yes
17 |  |  |  | Enhancement | Sometimes, the eye icon on the login screen is displayed twice, which is incorrect from a UI perspective. | No | No | No |  | No | No | Yes
18 |  |  |  | Issue | In the Search Company section, the company count is displayed differently compared to the Top Company Chart.For example, Dexcom company shows a count of 3109 in the Search section, while the Top Company Chart shows a count of 3106. | Yes | Yes | Yes |  | Yes | Yes | Yes
19 |  |  |  | Issue | (Organisation Curation)In the Company Innovation section, when I remove a recent source link, the link is not removed from the list. | Yes |  |  |  | No |  | No
20 |  |  |  | Issue | (Dashboard)The product count displayed on the tile is different from the count shown inside the screen. For example, the "Monitoring Metrics" tile shows 45 products, but when I click the same tile and open the Curated product section, only 34 products are displayed. | Yes | Yes | Yes |  | Yes | Yes | Yes
21 |  |  |  | Issue | Bayer Healthcare Company shows only 4 top focus area tiles, whereas the 5th tile is missing. | Yes | Yes | Yes |  | Yes | Yes | Yes
22 |  |  |  | Issue | (Top Focus Area)From Animas Corporation and all the companies listed below, either the top focus areas are missing or only 2 to 3 tiles are displayed, while there should be 5 tiles shown. | Yes | Yes | Yes |  | Yes | Yes | Yes
23 |  |  |  | Issue | (Eli Lilly and Co-Lilly)The Top Q-Factors of company patents are displayed incorrectly in the Top Patent section. For example, some patents show Q-Factor numbers as 772 and 770, but the Top Patent Chart shows the highest Q-Factor as 542, which is incorrect. | Yes | No | No |  | Yes | Yes | Yes
24 |  |  |  | Issue | (Dashboard)When I select any taxonomy tile, the curated patent button count and the tile count are displayed the same. However, when I click on the button, the count shown inside the screen is different. | Yes | Yes | No |  | Yes | No | No
25 |  |  |  | Enhancement | sometimes, the eye icon on the login screen is displayed twice, which is incorrect from a UI perspective. | Yes | Yes | Yes |  | Yes | Yes | Yes
26 |  |  |  | Issue | In the Rating and Ease of Detection fields, if I assign different ratings to multiple patents (e.g., 10 patents) and then delete the rating of just one patent, the ratings for all patents get deleted instead of only the selected one. | Yes | Yes | Yes |  | Yes | Yes | Yes
27 |  |  |  | Issue | I uploaded a claim chart in 1 curated patent, for example, by adding Cambridge Enterprises as the company. Later, in My Portfolio, I searched for the same company and clicked on the tile under Target Company with my selected company name. It showed 8 highly relevant patents, but when I clicked the button and checked inside the detailed screen, only 7 patents were displayed — 1 patent was missing. | Yes | Yes | Yes |  | Yes | Yes | Yes
28 |  |  |  | Issue | (View product Portfolio) Dexcom, Inc. shows 9 products, but on checking, only 8 are displayed — 1 product is missing. | Yes | Yes | Yes |  | Yes | Yes | No
29 |  |  |  | Issue | (LG Energy Solution) In the Top Patents section, some patents are showing a Q-Factor of 0. | Yes | Yes | Yes |  | Yes | Yes | Yes
30 |  |  |  | Issue | (Automobile) I added claim charts to 4 different patents, but in the Heatmap, only 2 patents are being displayed. | Yes |  |  |  | No |  | Yes
31 | 2025-10-08 |  |  | Issue | [Demo Portal]:When I select a Target Company/Product while uploading a Claim Chart, the company does not get selected. | No | Yes | Yes |  | Yes | Yes | Yes
32 |  |  |  | Issue | I added a claim chart to a patent, and it was uploaded successfully. But when I checked in the portfolio, the patent was missing from the Highly Relevant Patents" section. It only appears in the Heat Map, while the entire patent is not showing in the relevant section. | Yes | No |  |  | No |  | Yes
33 |  |  |  | Issue | I selected a taxonomy tile (EX-Component). The tile count was 26,135, and the Curated Patent button also showed the same count. After clicking the button, the Curated section displayed 26,094. When I selected All, it still showed 26,094 instead of the full count. This is incorrect, as some patents are missing. | Yes | No | No |  | No | No | No
34 | 2025-10-08 |  |  | Issue | [Demo Portal]:When I switch from the Curated section to the All section, the system takes a long time to load and then displays a red error message | No | No | Yes |  | Yes | Yes | No | #VALUE!
36 |  |  |  | Issue | From the American Diabetes Association onward, all the companies are displayed, but their products are missing. | Yes | No | Yes |  | Yes | Yes | Yes
37 |  |  |  | Issue | All data is missing from the Automobile (C) Workspace. | No | Yes | Yes |  | Yes | Yes | Yes
38 |  |  |  | Issue | In the Product Portfolio, for example, if I have a company named Airtel in My Portfolio and move it to Target Company using Reset to Default, it correctly shifts to the Target section. However, when I refresh the Product Portfolio screen, the company automatically returns to My Portfolio.This issue should not occur. The company should only move back from Target to My Portfolio if the user goes to the dashboard and then reopens Product Portfolio, not just by refreshing the same screen. | No | No | No |  | No | No | No
39 |  |  |  | Issue | In the Telecommunication (C) Workspace, the dashboard shows 1 uncurated patent, but inside the screen, it displays 7. | No | Yes | Yes |  | Yes | Yes | Yes
40 |  |  |  | Issue | In the Automobile Test, I selected patent EP1899605B1 and uploaded a claim chart with company Airtel and product Test Auto Fill. The claim chart appeared correctly in the Heat Map. Then, in Product Portfolio, I moved Airtel from My Portfolio to Target using Reset to Default. After this, the Highly Relevant Patents section showed 10 patents. Inside the screen, all 10 appeared, including my claim chart, which was correct. However, when I rechecked through the Curated Patent section: 4 of the 9 extra patents did not appear. 3 patents showed a different target company instead of Airtel, or a different product. This is an issue. | No |  |  |  | No
41 |  |  |  | Issue | In the Product Portfolio, I went to the Target Portfolio and selected my first company, Medtronic. Then I saw two tiles. Under Insulin Delivery Device, 14 products were displayed. After clicking, a third tile appeared named Minimed 780G Insulin Pump with a count of 16,891.When I clicked View Relevant Patents, the inside screen showed 16,886, which is incorrect. Going back and clicking the same tile opened a Technology tile with a count of 10,639. But when I clicked View Relevant Patents, the screen took a long time to load and then displayed a red error. | No | No | No |  | No |  | No
42 |  |  |  | Enhancement | In the Product Portfolio, the product tile chain is not working properly. For example, if I select multiple tiles and then try to return to the first tile by clicking on the No. 1 tag, it is not clickable. | No | No | No |  | No |  | No
43 |  |  |  | Enhancement | In the Product Portfolio, a search bar option is required. | No | No | No |  | No |  | No
44 |  |  |  | Issue | In Telecommunication (BMW) Company, the Key Market chart is missing data for Japan, but the Japan chart still shows 13%. | Yes | No | No |  | No |  | No
45 |  |  |  | Issue | In Telecommunication, the company Texas Instruments Incorporated is showing the same taxonomy tile twice. | Yes | Yes | No |  | Yes |  | Yes
46 |  |  |  | Issue | In Semiconductor, for the company Texas Instruments Incorporated, when I click on any taxonomy tile, the active patent families are not displayed, and the count shows 0. | Yes | Yes | Yes |  | Yes |  | Yes
47 |  |  |  | Issue | In the Waferfabric Workspace, the company Unimicron Technology Corporation is showing 34 un-curated patents. The first issue is that we have not added any data to this workspace, so it is unclear why patents are appearing under the Un-curated button. Secondly, when I click on the un-curated patents, the inside screen appears blank. | Yes | [5 empty] | Yes
48 |  |  |  | Issue | We are facing issues while uploading the taxonomy. | No | No | No |  | No |  | No
49 |  |  |  | Enhancement | Entering an invalid company name or taxonomy name does not trigger a pop-up message to inform the user | No | No | No |  | No |  | No
50 |  |  |  | Issue | In the Semiconductor Workspace, under Texas Instruments Incorporated, for the product part number ADC09QJ800-Q1, one additional technology feature is being displayed. | Yes |  | Yes
51 |  |  |  | Enhancement | In the Custom Column feature, when the data type is set to Hyperlink and a file is added, the system displays the message ‘Custom Column data successfully updated.’ However, when a file is deleted, the same message is shown, which is incorrect. The correct message in this case should be ‘Custom Column data successfully deleted. | No | No | No |  | No
52 |  |  |  | Issue | In the Semiconductor Workspace, under Ferrari Company, there are 6 curated patents, and the total family members for these patents are 11. Therefore, in the ‘All’ section, only 11 publications should be displayed. However, the system is currently showing 1,222 patents, which is incorrect | No |  |  |  | No |  |  | #VALUE!
53 |  |  |  | Enhancement | From a UI perspective, the design of this tile is not optimal for user visibility | No |  |  |  | No |  |  | #VALUE!
54 |  |  |  | Issue | In the Telecommunication Workspace Dashboard, the ‘Key Market’ section chart currently displays only 4 countries. One country, Japan, is missing. | No
55 |  |  |  | Issue | In the Telecommunication Workspace Dashboard, the ‘Key Market’ section shows Finland’s demography as 0.49%, but when I click on it, the detailed view is blank, which is incorrect. | No |  |  |  | No
56 |  |  |  | Issue | Telecommunication Workspace Dashboard – Portfolio Section Issue:In the Portfolio section, two companies are displayed: 1. Broadcom Inc. 2. Nokia Corporation, each showing one product on the company tile.When I click on Nokia Corporation, the “2 Highly Relevant Patents” button is shown. Clicking this button opens a screen displaying 3 patents, but the button only shows 2 patent numbers, which is inconsistent.Upon checking these 3 patents in the Curated Patent section to verify the company and product: Only 1 patent correctly shows Nokia as the target company and product. For the other 2 patents, both the target company and product are missing. Patent Numbers:WO2022233693A1, US11496205B2, US8238810B2 | No
57 |  |  |  | Issue | In the Telecommunication Workspace Dashboard, the Un-Curated Patent button shows 7 patents, but when open the screen, 8 patents are displayed. | No |  |  |  | Yes
58 |  |  |  | Issue | In the Semiconductor Workspace Dashboard, the Top Patent chart displays the patent number US12141073B1. However, when I search for this patent in the Curated Patent section (Unique, Curated, or All), it does not appear in any of these sections, even though it is visible in the Top Patent chart. | No |  |  |  | No |  |  | #VALUE!
59 |  |  |  | Issue | When I log in for the first time and select the ‘Remember for 30 days’ checkbox, the system does not autofill my ID and password on the next login. | No | No | No |  | No
60 |  |  |  | Issue | In the (Curated Patent section), when I search for any selected tag in the Focus Levels, it does not appear as selected, which is an issue. | No |  |  |  | No
61 |  |  |  | Issue | In the cases of companies such as Nvidia Corp, The TMRW Foundation, Disney, and Calany Holding SARL, when I select any taxonomy tile, the tile count and the Curated Patent button count match. However, inside the detailed screen, a higher count is displayed, which is incorrect. | Yes | Yes | No |  | No
62 |  |  |  | Issue | In the Licensing/Litigation section, when I upload any claim chart, it uploads successfully. However, when I try to view it, the chart opens but no features are visible, and the screen appears blank. If I cancel, the chart disappears from the screen, and after refreshing, it reappears but the issue remains the same. | Yes | Yes | No |  | Yes
63 |  |  |  | Issue | In the Curated Patent section, the Sort button is not functioning properly. | Yes | No | No |  | No
64 |  |  |  | Issue | For Patent ID US12223593B2 (Family ID 62708473), when I check in the Curated Patent section, it does not appear in the Unique section. The screen appears blank | No |  |  |  | No
65 |  |  |  | Issue | In the Heat Map section, when I try to click the ‘View’ or ‘Download’ button for a claim chart, the buttons do not respond, and a red error is displayed | No | No | No |  | No
66 |  |  |  | Enhancement | In the Heat Map section, error information messages should appear on the screen itself rather than behind the pop-up. | No |  |  |  | No
67 |  |  |  | Enhancement | When selecting a company from the dashboard, I can choose any company without patents. However, if I am already viewing a company and try to select another company without patents from there, it is not selectable. This should be allowed | No |  |  |  | No
68 |  |  |  | Issue | In the Heat Map section, when I access it from the Dashboard under Curated Patents, all claim charts for the patents are displayed, which is correct. However, when I access the Heat Map from a specific company’s product, it still shows all claim charts from all companies, just like the dashboard view. This is incorrect. When accessing Heat Map from a company, the patents should be filtered to display only that company’s claim charts to avoid confusion. | No |  |  |  | No
69 |  |  |  | Issue | For The TMRW Foundation company, the active patent family count shows 41 without selecting any tile, with the last update dated August 15, 2025. However, when I select a tile, the active patent count increases to 72. This indicates that the number 41 is incorrect, and the correct active patent count should be 72. | Yes | Yes | No |  | No
70 |  |  |  | Issue | In The TMRW Foundation company, patents belonging to Calany Holding SARL are being displayed, which is incorrect. | Yes | No | No |  | No
71 |  |  |  | Issue | In the Curated Product section, when I search for a product category (e.g., “Extended Reality”), an extra product from another category (e.g., “Electronic and Electric Equipment”) appears, which seems incorrect. | Yes | Yes | No |  | No |  |  | #VALUE!
72 |  |  |  | Issue | In the Curated Product section, when I hover over any subcategory, its full information does not appear like a proper pop-up, which is incorrect. |  |  | No
73 |  |  |  | Issue | In Calany Holding SARL, when navigating the Technology section, on the third tile named 3D Modeling, 24 patents are displayed. However, when checking the key market demographics, Japan shows 0%. Upon reviewing the 24 patents, I found that 2 of them are actually from Japan. | Yes | No | No |  | No
74 |  |  |  | Issue | In the Dashboard, after selecting Product Portfolio → Zero Density → Company and then the 5th tile Semi/Partially Immersive, the View Relevant Patent button shows 13 patents. However, upon clicking and viewing the details, it displays 3 highly relevant patents and 18 relevant patents, indicating an incorrect count. | No |  | No
75 |  |  |  | Issue | In Target Company, clicking beside the checkbox incorrectly shows a checkmark. Additionally, the checkbox itself should not get selected. | No | No | No |  | No
76 |  |  |  | Issue | The last update date is missing for some companies in the top comapny listing. | No | No | No |  | No
77 | 2025-10-09 |  |  | Issue | [Portfolio Demo] – Semiconductor Dashboard:In the Top Patents section, when I check the first patent under Curated Patents, the patent ID is US12141073B1. However, this patent is missing from both the Curated and Unique sections. When I check under the All section, the patent appears along with 12 duplicate patents.Additionally, when I check the Family ID 73456693, it shows approximately 725 duplicate patents. | No |  |  |  | No
78 |  |  |  | Issue | [Diabetic] – Product Portfolio:When I try to check the “View Relevant Patents” option for the Medtronic company, the screen takes a long time to load, and eventually, a red error message appears. |  | No |  |  | Yes |  |  | #VALUE!
79 |  |  |  | Enhancement | In the Taxonomy Upload UI, the sizes of all taxonomy tiles are not the same. | No |  |  |  | No |  |  | #VALUE!
80 | 2025-10-13 |  |  | Issue | In the Diabetic Portal (Curated Patent) section, when I select “All” and click on the Next Page arrow button, the screen takes a long time to load, and a red error message appears. | Yes | No |  |  | Yes |  |  | #VALUE!
81 | 2025-10-13 |  |  | Issue | [STF]The Premium Feature pop-up is incorrectly displayed in the Admin account. | Yes |  |  |  | Yes | Yes
82 | 2025-10-13 |  |  | Issue | [STF] Issue: The Report and WIP Report sections in the portal are not working when clicked. | Yes |  |  |  | Yes | Yes
83 | 2025-10-14 |  |  | Enhancement | [For all portals], in the Last Level, Additional Information, and Other columns, a taxonomy select pop-up should display some sample tags by default, without requiring the user to type anything. This will help users easily understand how to add taxonomy tags. | No | No | No |  | No | No |  | #VALUE!
84 | 2025-10-14 |  |  | Enhancement | [For all portals], in the Last Level, Additional Information, and Other columns, when a user types a letter or word in the taxonomy select pop-up (e.g., typing “T”), the pop-up should: First display tags that start with the typed letter/word (e.g., “Technology Tag” if it starts with “T”). Only show other matching tags afterward. If there is only one tag starting with the typed letter/word, it should appear first in the list, not in the second or third position. This will make it easier for users to find and select the relevant tags efficiently. | No | No | No |  | No | No |  | #VALUE!
85 | 2025-10-14 |  |  | Issue | [EDL Portal] – Highly relevant patent members are missing. | No |  |  |  | No |  |  | #VALUE!
86 | 2025-10-15 |  |  | Issue | [EDL] – (Curated Patent) – Select Column Filter: If I deselect the first three columns, then refresh the portal and select them again, the columns do not appear. | No |  |  |  | No
87 | 2025-10-16 |  |  | Issue | [EDL] – In the Curated Product section, when I use the filter and select some values, after clearing the filter completely, the previously selected values still appear when I try to search again. | No |  |  |  | No
88 | 2025-10-22 |  |  | Issue | [All Portals] – {Select Column}The “Publication Number” column should never be unselected by the user. This option should not be provided at any time, as all data depends on the patent number. | No | No | No | No | No | No
89 | 2025-10-22 |  |  | Enhancement | [All Portals] – We need a Serial Number column to track patents. | No |  |  |  | No
90 | 2025-10-22 |  |  | Enhancement | [All Portals] – {Filter Section}-If a user applies multiple filters, they should not have to delete the existing filters to add something new. Instead, the user should be able to edit the existing filters directly, making it easier and more convenient for them | No |  |  |  | No
91 | 2025-10-22 |  |  | Enhancement | [All Portals] – {Product Portfolio Section}We need an Expand button and a Search bar in all portals. | No |  |  |  | No
92 | 2025-10-22 |  |  | Enhancement | [All Portals] – The user should not be logged out automatically while using the portal. Automatic session timeout or logout should only occur if the user is inactive for more than 30 minutes. | No | No | No |  | No
93 | 2025-10-23 |  |  | Issue | [EDL Portal] – {Innovation and Filing Trend Section}If I select any taxonomy tile, e.g., Component, and then go to the Innovation and Filing Trend Section and select any Filing Innovation, the count displayed outside shows 218, while the count inside the screen shows 358. This is a count-mismatch issue. |  |  |  |  | No
94 | 2025-10-24 |  |  | Issue | [EDL] – Top Focus Area (Company: Vectorious): Some taxonomy entries under Top Focus Area are missing. |  |  |  |  | No
95 | 2025-10-24 |  |  | Issue | [EDL Portal] – The percentages displayed in the Key Market section are incorrect. |  |  |  |  | No
96 | 2025-10-24 |  |  | Issue | [IPRG – Dashboard] – The 3x3 matrix chart is being displayed on the portal even though it was not provided | [6 empty] | No
97 | 2025-10-24 |  |  | Issue | [IPRG] – “Curated Patent” button requires 2–3 clicks to respond after selecting a taxonomy tile. | [6 empty] | No
98 |  |  |  | Requirement | Need unique ¦ Curated ¦ All sections on highly and probable relevants patents screen
99 |  |  |  | Enhancement | {Items per Page}-If the number of patents available on the page is less than the selected category limit, the “Next ( > )” button should be unselectable/disabled so that it is not clickable.Example: When 25 patents per page are selected but only 19 patents are available, the Next button should remain disabled.
100 |  |  |  | Issue | Key Market Section-When I select a taxonomy (from the lower side of the taxonomy section), the Key Market section updates its data according to the selected tile. However, the flag for one demographic (East-Timor) is not displaying in that section.
101 | 2025-10-31 |  |  | Enhancement | Top Companies / Key Market Section-Both section containers are displaying with a smaller height. Additionally, the Key Market section is currently showing only 2 demographics, which is incorrect — it should display at least 5 demographics. The container sizes of both the Top Companies and the Key Market section are too small and need to be adjusted.
102 |  |  |  | Issue | Taxonomy / Dashboard Section-When I select a taxonomy, only the Key Market, Top Company, and Industry Active Status boxes expand to their actual size, which is correct. However, when I deselect the taxonomy, these boxes shrink back to a smaller size, which is incorrect behavior.
103 |  |  |  | Issue | After uploading a Claim Chart, when I go to the Heatmap section and delete the Claim Chart, it does not get removed from the Heatmap and still continues to display. After that, when I close the Heatmap and try to open the Claim Chart again by clicking View from the Associated Claim Chart section, the screen gets stuck | No
104 | 2025-11-11 |  |  | Issue | In the Immersive Workspace for NVIDIA Corp, the system My product portfolio shows a total of 191 products, but the top section displays “0 products”. Additionally, when I click on “View Product”, the inner product details screen appears blank.
105 | 2025-11-11 |  |  | Issue | The Back button on the Dashboard is currently not functioning.
106 | 2025-11-12 |  |  | Issue | When I upload the patent US20040248204A1 in the Diabetic Portal, the system accepts it successfully and shows pop-ups indicating that the patent is uncurated and that the dashboard is being prepared. However, after upload, the patent does not appear in the Uncurated Patent section but is visible under Curated → All. Additionally, when I upload the same patent again, the system allows it without any warning that the patent already exists. This is a major issue that needs to be resolved. |  | No
107 |  |  |  | Issue | In the Diabetic Portal (Uncurated Patents), there were already 2 uncurated patents in the system. After that, I uploaded 71 more patents, which the system successfully accepted and showed a pop-up saying they would appear in the Uncurated section. The total count became 73. Then I selected 3 patents to delete, but the system deleted all uncurated patents. When I tried re-uploading the file, the system said there are already 73 uncurated patents, but when I check the Uncurated section, it shows 0. |  | No
108 | 2025-11-17 |  |  | Issue | If I save a report with the same name in two different modules—for example, one from the Curated Patent section and the second from the Uncurated Patent section—only one report appears in the Reports section. The second report is missing.
109 | 2025-11-18 |  |  | Issue | In the Product Data Edit section, we currently have the Technology feature set. Currently, the Level 1 (1), Level 2 (1.1), and Level 3 (1.1.1) are all mandatory fields. This is not necessarily true because the Level 3 (1.1.1) tag will not always be available. In such cases, when I try to save the product, the system shows a red error.The correct behaviour should be that Level 1 and Level 2 are mandatory, but Level 3 (1.1.1) should be optional. If a Level 3 tag is not available, I should still be able to save the product without receiving an error. | [7 empty] | #VALUE!
110 |  |  |  | Issue | (YDC-Portal – Organisation Curation Page) When I add a new company and fill in all the required information, after clicking Save, the screen gets stuck on the loading loop.

## architecture_issues
Sno. | Date | Repetitive Count | Repetitive Dates | Type | Issue | Status | image | Video | Remarks | Dev Status
1 |  |  |  | Issue | (Curated Patent)When clicking the Column Dropdown, selecting and then unselecting "Publication Number" and "Other Publication Number" columns causes the left-side columns (Family Grouping and Multiple Patent Select) to disappear when scrolling. | Yes
2 |  |  |  | Enhancement | (Curated Patent) If I set "Patents per Page" to 100 and delete a patent, it automatically resets to 25.When I set it back to 100 and restore a patent, it again defaults to 25 automatically. | No
3 |  |  |  | Enhancement | (Curated Patent)In the Rating and Ease of Detection sections, when deleting a selected comment, the system shows "Update successfully, The correct message should be "Successfully deleted".
4 |  |  |  | Issue | When searching by patent publication date in the search section, the screen remains empty after loading.
5 |  |  |  | Issue | (Curated Patent) Sometimes, when selecting Product/Company in the Licensing/Litigation section, the screen appears empty.
6 |  |  |  | Issue | (Curated Patent)In the Focus Level section, the tag limit should be 40 characters.However, if I enter more than 40 characters, the Upload button remains clickable, which is incorrect.
7 | 2025-09-09 | 2 | 9/9/2025 ¦ 13-10-2025 | Issue | We receive a red error when adding a new tag, and the Delete and Undo buttons also do not work, showing a red error. |  | #VALUE!
8 |  |  |  | Enhancement | (Organisation Curation)In the Organisation Curation section, if I add a new company without providing a Company URL, why does the system still display a LinkedIn link?
9 |  |  |  | Issue | (Organisation Curation)In the Organisation Curation section, after filling all the required fields and saving the company, the Company Innovation field appears with pre-selected value, However, the selected Company Innovation fields are not visible.
10 |  |  |  | Issue | (Organisation Curation)In the Company Innovation fields, at Level 2, some categories/tags are shown multiple times.This is incorrect, as each category/tag should appear in only one group. |  | #VALUE!
11 | 2025-08-10 |  |  | Issue | [Portfolio Demo] – Automobile, Automobile Test :When I go to the Un-curated Patents section and select a patent, I proceed to add its Focus Level and Last Level to convert it from an uncurated to a curated patent. However, when I try to add tags, a red error message appears.
12 | 2025-08-10 |  |  | Issue | [Portfolio Demo] – Automobile Test (Organizing Curation – Company Innovation):When I try to add any link, a red error message appears first. After that, a confirmation message appears indicating that the company link has been successfully saved.
13 | 2025-08-10 |  |  | Issue | [Portfolio Demo] – Automobile Test (Organizing Curation – Company Innovation):When I delete any link, it is successfully removed; however, the associated date is not deleted. |  | #VALUE!
14 | 2025-08-10 |  |  | Red Error | [Diabetic] – US2025082840A1:This is an un-curated patent. I curated this patent by adding the Last Level to verify the movement, which was completed successfully. After that, I searched for the patent in the Curated section and confirmed that it appeared correctly, but I searched with Patent ID Red error show. Next, to move it back from Curated to Un-curated, I deleted the Last Level and checked the movement, which was also completed successfully. Finally, I searched for the patent to ensure there were no duplicates in the Curated section. However, when I checked this patent under the ALL section, after waiting for a long loading time, a red error appeared, which should not have occurred. |  | #VALUE!
15 |  |  |  | Issue | After adding a new company and checking the Dashboard, the 3x3 chart is displayed below the Key Market section.
16 |  |  |  | Issue | (Curated Products)If I add a taxonomy in the Last Level section of a product, the screen keeps loading indefinitely.
17 |  |  |  | Enhancement | Sometimes, the eye icon on the login screen is displayed twice, which is incorrect from a UI perspective.
18 |  |  |  | Issue | In the Search Company section, the company count is displayed differently compared to the Top Company Chart.For example, Dexcom company shows a count of 3109 in the Search section, while the Top Company Chart shows a count of 3106.
19 |  |  |  | Issue | (Organisation Curation)In the Company Innovation section, when I remove a recent source link, the link is not removed from the list.
20 |  |  |  | Issue | (Dashboard)The product count displayed on the tile is different from the count shown inside the screen. For example, the "Monitoring Metrics" tile shows 45 products, but when I click the same tile and open the Curated product section, only 34 products are displayed.
21 |  |  |  | Issue | Bayer Healthcare Company shows only 4 top focus area tiles, whereas the 5th tile is missing.
22 |  |  |  | Issue | (Top Focus Area)From Animas Corporation and all the companies listed below, either the top focus areas are missing or only 2 to 3 tiles are displayed, while there should be 5 tiles shown.
23 |  |  |  | Issue | (Eli Lilly and Co-Lilly)The Top Q-Factors of company patents are displayed incorrectly in the Top Patent section. For example, some patents show Q-Factor numbers as 772 and 770, but the Top Patent Chart shows the highest Q-Factor as 542, which is incorrect.
24 |  |  |  | Issue | (Dashboard)When I select any taxonomy tile, the curated patent button count and the tile count are displayed the same. However, when I click on the button, the count shown inside the screen is different.
25 |  |  |  | Enhancement | sometimes, the eye icon on the login screen is displayed twice, which is incorrect from a UI perspective.
26 |  |  |  | Issue | In the Rating and Ease of Detection fields, if I assign different ratings to multiple patents (e.g., 10 patents) and then delete the rating of just one patent, the ratings for all patents get deleted instead of only the selected one.
27 |  |  |  | Issue | I uploaded a claim chart in 1 curated patent, for example, by adding Cambridge Enterprises as the company. Later, in My Portfolio, I searched for the same company and clicked on the tile under Target Company with my selected company name. It showed 8 highly relevant patents, but when I clicked the button and checked inside the detailed screen, only 7 patents were displayed — 1 patent was missing.
28 |  |  |  | Issue | (View product Portfolio) Dexcom, Inc. shows 9 products, but on checking, only 8 are displayed — 1 product is missing.
29 |  |  |  | Issue | (LG Energy Solution) In the Top Patents section, some patents are showing a Q-Factor of 0.
30 |  |  |  | Issue | (Automobile) I added claim charts to 4 different patents, but in the Heatmap, only 2 patents are being displayed.
31 | 2025-10-08 |  |  | Issue | [Demo Portal]:When I select a Target Company/Product while uploading a Claim Chart, the company does not get selected.
32 |  |  |  | Issue | I added a claim chart to a patent, and it was uploaded successfully. But when I checked in the portfolio, the patent was missing from the Highly Relevant Patents" section. It only appears in the Heat Map, while the entire patent is not showing in the relevant section.
33 |  |  |  | Issue | I selected a taxonomy tile (EX-Component). The tile count was 26,135, and the Curated Patent button also showed the same count. After clicking the button, the Curated section displayed 26,094. When I selected All, it still showed 26,094 instead of the full count. This is incorrect, as some patents are missing.
34 | 2025-10-08 |  |  | Issue | [Demo Portal]:When I switch from the Curated section to the All section, the system takes a long time to load and then displays a red error message |  | #VALUE!
36 |  |  |  | Issue | From the American Diabetes Association onward, all the companies are displayed, but their products are missing.
37 |  |  |  | Issue | All data is missing from the Automobile (C) Workspace.
38 |  |  |  | Issue | In the Product Portfolio, for example, if I have a company named Airtel in My Portfolio and move it to Target Company using Reset to Default, it correctly shifts to the Target section. However, when I refresh the Product Portfolio screen, the company automatically returns to My Portfolio.This issue should not occur. The company should only move back from Target to My Portfolio if the user goes to the dashboard and then reopens Product Portfolio, not just by refreshing the same screen.
39 |  |  |  | Issue | In the Telecommunication (C) Workspace, the dashboard shows 1 uncurated patent, but inside the screen, it displays 7.
40 |  |  |  | Issue | In the Automobile Test, I selected patent EP1899605B1 and uploaded a claim chart with company Airtel and product Test Auto Fill. The claim chart appeared correctly in the Heat Map. Then, in Product Portfolio, I moved Airtel from My Portfolio to Target using Reset to Default. After this, the Highly Relevant Patents section showed 10 patents. Inside the screen, all 10 appeared, including my claim chart, which was correct. However, when I rechecked through the Curated Patent section: 4 of the 9 extra patents did not appear. 3 patents showed a different target company instead of Airtel, or a different product. This is an issue.
41 |  |  |  | Issue | In the Product Portfolio, I went to the Target Portfolio and selected my first company, Medtronic. Then I saw two tiles. Under Insulin Delivery Device, 14 products were displayed. After clicking, a third tile appeared named Minimed 780G Insulin Pump with a count of 16,891.When I clicked View Relevant Patents, the inside screen showed 16,886, which is incorrect. Going back and clicking the same tile opened a Technology tile with a count of 10,639. But when I clicked View Relevant Patents, the screen took a long time to load and then displayed a red error.
42 |  |  |  | Enhancement | In the Product Portfolio, the product tile chain is not working properly. For example, if I select multiple tiles and then try to return to the first tile by clicking on the No. 1 tag, it is not clickable.
43 |  |  |  | Enhancement | In the Product Portfolio, a search bar option is required.
44 |  |  |  | Issue | In Telecommunication (BMW) Company, the Key Market chart is missing data for Japan, but the Japan chart still shows 13%.
45 |  |  |  | Issue | In Telecommunication, the company Texas Instruments Incorporated is showing the same taxonomy tile twice.
46 |  |  |  | Issue | In Semiconductor, for the company Texas Instruments Incorporated, when I click on any taxonomy tile, the active patent families are not displayed, and the count shows 0.
47 |  |  |  | Issue | In the Waferfabric Workspace, the company Unimicron Technology Corporation is showing 34 un-curated patents. The first issue is that we have not added any data to this workspace, so it is unclear why patents are appearing under the Un-curated button. Secondly, when I click on the un-curated patents, the inside screen appears blank.
48 |  |  |  | Issue | We are facing issues while uploading the taxonomy.
49 |  |  |  | Enhancement | Entering an invalid company name or taxonomy name does not trigger a pop-up message to inform the user
50 |  |  |  | Issue | In the Semiconductor Workspace, under Texas Instruments Incorporated, for the product part number ADC09QJ800-Q1, one additional technology feature is being displayed.
51 |  |  |  | Enhancement | In the Custom Column feature, when the data type is set to Hyperlink and a file is added, the system displays the message ‘Custom Column data successfully updated.’ However, when a file is deleted, the same message is shown, which is incorrect. The correct message in this case should be ‘Custom Column data successfully deleted.
52 |  |  |  | Issue | In the Semiconductor Workspace, under Ferrari Company, there are 6 curated patents, and the total family members for these patents are 11. Therefore, in the ‘All’ section, only 11 publications should be displayed. However, the system is currently showing 1,222 patents, which is incorrect |  | #VALUE!
53 |  |  |  | Enhancement | From a UI perspective, the design of this tile is not optimal for user visibility |  | #VALUE!
54 |  |  |  | Issue | In the Telecommunication Workspace Dashboard, the ‘Key Market’ section chart currently displays only 4 countries. One country, Japan, is missing.
55 |  |  |  | Issue | In the Telecommunication Workspace Dashboard, the ‘Key Market’ section shows Finland’s demography as 0.49%, but when I click on it, the detailed view is blank, which is incorrect.
56 |  |  |  | Issue | Telecommunication Workspace Dashboard – Portfolio Section Issue:In the Portfolio section, two companies are displayed: 1. Broadcom Inc. 2. Nokia Corporation, each showing one product on the company tile.When I click on Nokia Corporation, the “2 Highly Relevant Patents” button is shown. Clicking this button opens a screen displaying 3 patents, but the button only shows 2 patent numbers, which is inconsistent.Upon checking these 3 patents in the Curated Patent section to verify the company and product: Only 1 patent correctly shows Nokia as the target company and product. For the other 2 patents, both the target company and product are missing. Patent Numbers:WO2022233693A1, US11496205B2, US8238810B2
57 |  |  |  | Issue | In the Telecommunication Workspace Dashboard, the Un-Curated Patent button shows 7 patents, but when open the screen, 8 patents are displayed.
58 |  |  |  | Issue | In the Semiconductor Workspace Dashboard, the Top Patent chart displays the patent number US12141073B1. However, when I search for this patent in the Curated Patent section (Unique, Curated, or All), it does not appear in any of these sections, even though it is visible in the Top Patent chart. |  | #VALUE!
59 |  |  |  | Issue | When I log in for the first time and select the ‘Remember for 30 days’ checkbox, the system does not autofill my ID and password on the next login.
60 |  |  |  | Issue | In the (Curated Patent section), when I search for any selected tag in the Focus Levels, it does not appear as selected, which is an issue.
61 |  |  |  | Issue | In the cases of companies such as Nvidia Corp, The TMRW Foundation, Disney, and Calany Holding SARL, when I select any taxonomy tile, the tile count and the Curated Patent button count match. However, inside the detailed screen, a higher count is displayed, which is incorrect.
62 |  |  |  | Issue | In the Licensing/Litigation section, when I upload any claim chart, it uploads successfully. However, when I try to view it, the chart opens but no features are visible, and the screen appears blank. If I cancel, the chart disappears from the screen, and after refreshing, it reappears but the issue remains the same.
63 |  |  |  | Issue | In the Curated Patent section, the Sort button is not functioning properly.
64 |  |  |  | Issue | For Patent ID US12223593B2 (Family ID 62708473), when I check in the Curated Patent section, it does not appear in the Unique section. The screen appears blank
65 |  |  |  | Issue | In the Heat Map section, when I try to click the ‘View’ or ‘Download’ button for a claim chart, the buttons do not respond, and a red error is displayed
66 |  |  |  | Enhancement | In the Heat Map section, error information messages should appear on the screen itself rather than behind the pop-up.
67 |  |  |  | Enhancement | When selecting a company from the dashboard, I can choose any company without patents. However, if I am already viewing a company and try to select another company without patents from there, it is not selectable. This should be allowed
68 |  |  |  | Issue | In the Heat Map section, when I access it from the Dashboard under Curated Patents, all claim charts for the patents are displayed, which is correct. However, when I access the Heat Map from a specific company’s product, it still shows all claim charts from all companies, just like the dashboard view. This is incorrect. When accessing Heat Map from a company, the patents should be filtered to display only that company’s claim charts to avoid confusion.
69 |  |  |  | Issue | For The TMRW Foundation company, the active patent family count shows 41 without selecting any tile, with the last update dated August 15, 2025. However, when I select a tile, the active patent count increases to 72. This indicates that the number 41 is incorrect, and the correct active patent count should be 72.
70 |  |  |  | Issue | In The TMRW Foundation company, patents belonging to Calany Holding SARL are being displayed, which is incorrect.
71 |  |  |  | Issue | In the Curated Product section, when I search for a product category (e.g., “Extended Reality”), an extra product from another category (e.g., “Electronic and Electric Equipment”) appears, which seems incorrect. |  | #VALUE!
72 |  |  |  | Issue | In the Curated Product section, when I hover over any subcategory, its full information does not appear like a proper pop-up, which is incorrect.
73 |  |  |  | Issue | In Calany Holding SARL, when navigating the Technology section, on the third tile named 3D Modeling, 24 patents are displayed. However, when checking the key market demographics, Japan shows 0%. Upon reviewing the 24 patents, I found that 2 of them are actually from Japan.
74 |  |  |  | Issue | In the Dashboard, after selecting Product Portfolio → Zero Density → Company and then the 5th tile Semi/Partially Immersive, the View Relevant Patent button shows 13 patents. However, upon clicking and viewing the details, it displays 3 highly relevant patents and 18 relevant patents, indicating an incorrect count.
75 |  |  |  | Issue | In Target Company, clicking beside the checkbox incorrectly shows a checkmark. Additionally, the checkbox itself should not get selected.
76 |  |  |  | Issue | The last update date is missing for some companies in the top comapny listing.
77 | 2025-10-09 |  |  | Issue | [Portfolio Demo] – Semiconductor Dashboard:In the Top Patents section, when I check the first patent under Curated Patents, the patent ID is US12141073B1. However, this patent is missing from both the Curated and Unique sections. When I check under the All section, the patent appears along with 12 duplicate patents.Additionally, when I check the Family ID 73456693, it shows approximately 725 duplicate patents.
78 |  |  |  | Issue | [Diabetic] – Product Portfolio:When I try to check the “View Relevant Patents” option for the Medtronic company, the screen takes a long time to load, and eventually, a red error message appears. |  | #VALUE!
79 |  |  |  | Enhancement | In the Taxonomy Upload UI, the sizes of all taxonomy tiles are not the same. |  | #VALUE!
80 | 2025-10-13 |  |  | Issue | In the Diabetic Portal (Curated Patent) section, when I select “All” and click on the Next Page arrow button, the screen takes a long time to load, and a red error message appears. |  | #VALUE!
81 | 2025-10-13 |  |  | Issue | [STF]The Premium Feature pop-up is incorrectly displayed in the Admin account.
82 | 2025-10-13 |  |  | Issue | [STF] Issue: The Report and WIP Report sections in the portal are not working when clicked.
83 | 2025-10-14 |  |  | Enhancement | [For all portals], in the Last Level, Additional Information, and Other columns, a taxonomy select pop-up should display some sample tags by default, without requiring the user to type anything. This will help users easily understand how to add taxonomy tags. |  | #VALUE!
84 | 2025-10-14 |  |  | Enhancement | [For all portals], in the Last Level, Additional Information, and Other columns, when a user types a letter or word in the taxonomy select pop-up (e.g., typing “T”), the pop-up should: First display tags that start with the typed letter/word (e.g., “Technology Tag” if it starts with “T”). Only show other matching tags afterward. If there is only one tag starting with the typed letter/word, it should appear first in the list, not in the second or third position. This will make it easier for users to find and select the relevant tags efficiently. |  | #VALUE!
85 | 2025-10-14 |  |  | Issue | [EDL Portal] – Highly relevant patent members are missing. |  | #VALUE!
86 | 2025-10-15 |  |  | Issue | [EDL] – (Curated Patent) – Select Column Filter: If I deselect the first three columns, then refresh the portal and select them again, the columns do not appear.
87 | 2025-10-16 |  |  | Issue | [EDL] – In the Curated Product section, when I use the filter and select some values, after clearing the filter completely, the previously selected values still appear when I try to search again.
88 | 2025-10-22 |  |  | Issue | [All Portals] – {Select Column}The “Publication Number” column should never be unselected by the user. This option should not be provided at any time, as all data depends on the patent number.
89 | 2025-10-22 |  |  | Enhancement | [All Portals] – We need a Serial Number column to track patents.
90 | 2025-10-22 |  |  | Enhancement | [All Portals] – {Filter Section}-If a user applies multiple filters, they should not have to delete the existing filters to add something new. Instead, the user should be able to edit the existing filters directly, making it easier and more convenient for them
91 | 2025-10-22 |  |  | Enhancement | [All Portals] – {Product Portfolio Section}We need an Expand button and a Search bar in all portals.
92 | 2025-10-22 |  |  | Enhancement | [All Portals] – The user should not be logged out automatically while using the portal. Automatic session timeout or logout should only occur if the user is inactive for more than 30 minutes.
93 | 2025-10-23 |  |  | Issue | [EDL Portal] – {Innovation and Filing Trend Section}If I select any taxonomy tile, e.g., Component, and then go to the Innovation and Filing Trend Section and select any Filing Innovation, the count displayed outside shows 218, while the count inside the screen shows 358. This is a count-mismatch issue.
94 | 2025-10-24 |  |  | Issue | [EDL] – Top Focus Area (Company: Vectorious): Some taxonomy entries under Top Focus Area are missing.
95 | 2025-10-24 |  |  | Issue | [EDL Portal] – The percentages displayed in the Key Market section are incorrect.
96 | 2025-10-24 |  |  | Issue | [IPRG – Dashboard] – The 3x3 matrix chart is being displayed on the portal even though it was not provided
97 | 2025-10-24 |  |  | Issue | [IPRG] – “Curated Patent” button requires 2–3 clicks to respond after selecting a taxonomy tile.
98 |  |  |  | Requirement | Need unique ¦ Curated ¦ All sections on highly and probable relevants patents screen
99 |  |  |  | Enhancement | {Items per Page}-If the number of patents available on the page is less than the selected category limit, the “Next ( > )” button should be unselectable/disabled so that it is not clickable.Example: When 25 patents per page are selected but only 19 patents are available, the Next button should remain disabled.
100 |  |  |  | Issue | Key Market Section-When I select a taxonomy (from the lower side of the taxonomy section), the Key Market section updates its data according to the selected tile. However, the flag for one demographic (East-Timor) is not displaying in that section.
101 | 2025-10-31 |  |  | Enhancement | Top Companies / Key Market Section-Both section containers are displaying with a smaller height. Additionally, the Key Market section is currently showing only 2 demographics, which is incorrect — it should display at least 5 demographics. The container sizes of both the Top Companies and the Key Market section are too small and need to be adjusted.
102 |  |  |  | Issue | Taxonomy / Dashboard Section-When I select a taxonomy, only the Key Market, Top Company, and Industry Active Status boxes expand to their actual size, which is correct. However, when I deselect the taxonomy, these boxes shrink back to a smaller size, which is incorrect behavior.
103 |  |  |  | Issue | After uploading a Claim Chart, when I go to the Heatmap section and delete the Claim Chart, it does not get removed from the Heatmap and still continues to display. After that, when I close the Heatmap and try to open the Claim Chart again by clicking View from the Associated Claim Chart section, the screen gets stuck
104 | 2025-11-11 |  |  | Issue | In the Immersive Workspace for NVIDIA Corp, the system My product portfolio shows a total of 191 products, but the top section displays “0 products”. Additionally, when I click on “View Product”, the inner product details screen appears blank.
105 | 2025-11-11 |  |  | Issue | The Back button on the Dashboard is currently not functioning.
106 | 2025-11-12 |  |  | Issue | When I upload the patent US20040248204A1 in the Diabetic Portal, the system accepts it successfully and shows pop-ups indicating that the patent is uncurated and that the dashboard is being prepared. However, after upload, the patent does not appear in the Uncurated Patent section but is visible under Curated → All. Additionally, when I upload the same patent again, the system allows it without any warning that the patent already exists. This is a major issue that needs to be resolved.
107 |  |  |  | Issue | In the Diabetic Portal (Uncurated Patents), there were already 2 uncurated patents in the system. After that, I uploaded 71 more patents, which the system successfully accepted and showed a pop-up saying they would appear in the Uncurated section. The total count became 73. Then I selected 3 patents to delete, but the system deleted all uncurated patents. When I tried re-uploading the file, the system said there are already 73 uncurated patents, but when I check the Uncurated section, it shows 0.
108 | 2025-11-17 |  |  | Issue | If I save a report with the same name in two different modules—for example, one from the Curated Patent section and the second from the Uncurated Patent section—only one report appears in the Reports section. The second report is missing.
109 | 2025-11-18 |  |  | Issue | In the Product Data Edit section, we currently have the Technology feature set. Currently, the Level 1 (1), Level 2 (1.1), and Level 3 (1.1.1) are all mandatory fields. This is not necessarily true because the Level 3 (1.1.1) tag will not always be available. In such cases, when I try to save the product, the system shows a red error.The correct behaviour should be that Level 1 and Level 2 are mandatory, but Level 3 (1.1.1) should be optional. If a Level 3 tag is not available, I should still be able to save the product without receiving an error. |  | #VALUE!
110 |  |  |  | Issue | (YDC-Portal – Organisation Curation Page) When I add a new company and fill in all the required information, after clicking Save, the screen gets stuck on the loading loop.